Государственное учреждение «Поставский территориальный центр социального обслуживания населения»

Гуманитарный проект

«Мы поможем»

| 1. Наименование проекта: «Мы поможем» |  |
| --- | --- |
| 2. Срок реализации: 12 месяцев |  |
| 3.Организация-заявитель, предлагающая проект: Государственное учреждение «Поставский территориальный центр социального обслуживания населения» |  |
| - 4. Цель проекта: Обеспечить потребность семей, воспитывающих детей-инвалидов средствами реабилитации и интерактивными развивающими играми и материалами, создать условия для максимально возможного развития их жизнеспособности. |  |
| 5. Задачи, планируемые к выполнению в рамках реализации проекта: 5.1. Повысить уровень и качество жизни детей-инвалидов Поставского района. 5.2. Создать бесплатный пункт прокат технических средств социальной реабилитации и развивающих игр для семей, воспитывающих детей-инвалидов. 5.3. Привлечь волонтеров в активную деятельность, направленную на поддержку целевой группы. |  |
| 6. Описание деятельности в рамках проекта в соответствии с поставленными задачами: 6.1. Обустройство помещения для пункта проката технических средств социальной реабилитации и развивающих игр. 6.2. Приобретение технических средств социальной реабилитации (степпер, тренажеры различной модификации, механическая беговая дорожка, тренажер-ходики, велотренажер детский, тренажер для осанки, дорожка здоровья, детский батут для координации движения, массажные мячики, массажные коврики, баланс-платформа и т.д.) для детей-инвалидов с заболеваниями опорно-двигательного аппарата. 6.3. Приобретение развивающего материала, интерактивных развивающих игр (настольно-развивающие игры, дидактические игры, обучающие игры и т.д.) для детей-инвалидов с особенностями психофизического развития. 6.4. Изготовление и распространение печатной продукции, информации в средствах массовой информации об открытии пункта проката. 6.5. Вовлечение граждан для оказания волонтерской детальности в рамках деятельности проекта. |  |
| 7. Целевая группа: семьи, воспитывающие ребенка-инвалида. |  |
| 8. В Поставском районе проживает 147 семей, воспитывающих детей-инвалидов. Для данной категории семей приобретение тренажеров для физического развития и детских развивающих принадлежностей становится проблемой. Материальное положение семьи, с появлением в ней ребенка-инвалида ухудшается, так как родитель занят уходом, не работает, а содержание и уход за ребенком-инвалидом требует больше средств, чем уход и содержание здорового ребенка. Возможность взять на безвозмездной основе во временное пользование тренажеры для физического развития или детские развивающие принадлежности позволят семьям сэкономить семейный бюджет, при этом воспользоваться необходимыми средствами реабилитации, удовлетворить потребность в развивающем оборудовании, снять социальную напряженность. У детей будет возможность пользоваться различными тренажерами и интерактивными играми на всех этапах развития для формирования определенных навыков, развития познавательных процессов, формирования представлений об окружающем мире. Актуальность проекта состоит в том, что развитие дополнительных социальных услуг будет являться эффективной и дополняющей формой социальной работы с семьями, воспитывающих детей-инвалидов. |  |
| 9. Общий объем финансирования (в долларах США): |  |
| Источник финансирования | Объем финансирования (в долларах США) |
| Средства донора | 7500 долларов |
| Софинансирование | 500 долларов |
| 10. Место реализации проекта (область, район, город): Республика Беларусь, Витебская область, г.Поставы |  |
| 11. Контактное лицо: инициалы, фамилия, должность, телефон, адрес электронной почты Качакулян Татьяна Вячеславовна, заведующий отделением комплексной поддержки в кризисной ситуации, телефон: +375 2155 25002 e-mail: postavy.r-tc@mintrud.by |  |

State Institution "Postavy Territorial Center for Social Services for the Population"

Humanitarian project

"We will help"

| 1. Project name: "We will help" |  |
| --- | --- |
| 2. Implementation period: 12 months |  |
| 3. Applicant organization proposing the project: State Institution "Postavy territorial center for social services for the population" |  |
| 4. The purpose of the project: to meet the needs of families raising children with disabilities with rehabilitation means and interactive educational games and materials, to create conditions for the maximum possible development of their vitality. |  |
| 5. Project objectives: 5.1. Improve the standard and quality of life of children with disabilities in the Postavy District. 5.2. Establish a free rental center for technical social rehabilitation equipment and educational games for families raising children with disabilities. 5.3. Engage volunteers in active support activities for the target group. |  |
| 6. Description of project activities in accordance with the stated objectives: 6.1. Construction of premises for a rental center for technical equipment for social rehabilitation and educational games. 6.2. Acquisition of technical means of social rehabilitation (stepper, exercise machines of various modifications, mechanical treadmill, exercise walker, children's exercise bike, posture trainer, health track, children's trampoline for movement coordination, massage balls, massage mats, balance platform, etc.) for children with disabilities with musculoskeletal disorders. 6.3. Purchase of developmental materials, interactive developmental games (board games, didactic games, educational games, etc.) for children with disabilities and special psychophysical development needs. 6.4. Production and distribution of printed materials and information in the media about the opening of the rental center. 6.5. Engagement of citizens to provide volunteer support for the project. |  |
| 7. Target group: families raising a disabled child. |  |
| 8. There are 147 families raising children with disabilities in the Postavy District. For these families, acquiring exercise equipment and educational supplies for children is a challenge. The financial situation of a family worsens with the appearance of a disabled child, since the parent is busy with care, does not work, and the maintenance and care of a disabled child requires more funds than the care and maintenance of a healthy child. The opportunity to borrow physical exercise equipment or children's developmental supplies free of charge allows families to save money while enjoying essential rehabilitation resources, satisfying the need for developmental equipment, and alleviating social tension. Children will have the opportunity to use various training equipment and interactive games at all stages of development to develop specific skills, enhance cognitive processes, and develop understanding of the world around them. The relevance of the project lies in the fact that the development of additional social services will be an effective and complementary form of social work with families raising children with disabilities. |  |
| 9. Total funding (in US dollars): |  |
| Source of financing | Amount of financing (in US dollars) |
| Donor funds | $ 7,500 |
| Co-financing | $ 500 |
| 10. Location of the project (region, district, city): Republic of Belarus, Vitebsk region, Postavy |  |
| 11. The contact person: initials, surname, position, phone number, e-mail address Tatyana Vyacheslavovna Kachakulyan, Head of the Comprehensive Crisis Support Department, phone: +375 2155 25002 e-mail: postavy.r-tc@mintrud.by |  |